## Requirements
I. Requirements
Ngày nay việc học trực tuyến đã không còn quá xa lạ với chúng ta. Nhất là trong giai đoạn dịch covid phải ở nhà. Bên cạnh việc học thì đòi hỏi phải có những bài kiểm tra để đánh giá kết quả học tập Vì vậy chúng tôi đã xây dựng một trang web quản lý thi trắc nghiệm để thầy cô và học sinh tiện cho việc học và kiểm tra của mình Hệ thống đảm bảo bảo mật thông tin người dùng, sự minh bạch rõ ràng trong đáp án đề thi và quá trình thi cử Ngoài ra, còn giúp giảm tải công việc cho thầy cô trong việc chấm điểm bài thi và thuận tiện cho việc thi cử ở mọi nơi

## Team
TEAM DEVELOPMENT STRUCTURE
No. | Name | Account | Roles | DateStart | Date End
1 | Nguyễn Phạm Hữu Tài | lorenkid107 | Product Owner | 16/2/2023
2 | Lê Hoài Thanh Huy | Huyle | ScrumMaster | 16/2/2023
3 | Nguyễn Phạm Hữu Tài | lorenkid107 | Team Lead | 17/2/2023
3 | Nguyễn Phan Tấn Tài | Tainguyenphan | Dev | 17/2/2023
5 | Lê Hoài Thanh Huy | Huyle | Dev | 17/2/2023

## Product backlog
Online Test Manager Project - PRODUCT BACKLOG
Story ID | Story Name | Points
61
Actor: Student
1 | Login | 2
2 | View Class | 3
3 | View Subject | 3
4 | View Personal Information | 3
5 | View HomePage | 3
6 | Logout | 1
Actor: Teacher
7 | Login | 2
8 | Create exam questions | 4
9 | View Class | 3
10 | View Subject | 3
11 | Logout | 1
Actor: System Management
12 | User Management | 5
13 | Test Management | 6
14 | Class Management | 5
15 | Course Management | 5
16 | Subject Management | 5
17 | Examination Management (Create,Update) | 6
18 | Login | 2
19 | Logout | 1

## Sprint backlog
Online Test Manager Project - SPRINT BACKLOG
Story ID | Story Name | Points | Name Of Dev | Start Date | Endate | Act Start Date | ActEndate | Act Points | Notes
51
Sprint 1
1 | Login | 2 | Tấn Tài
2 | View Class | 3 | Hữu Tài
3 | View Subject | 3 | Huy
4 | View Personal Information | 3 | Tấn Tài
5 | View HomePage | 3 | Huy
6 | Logout | 1 | Tấn Tài
Sprint 2
7 | Create exam questions | 4 | Huy
8 | User Management | 5 | Tấn Tài
9 | Test Management | 6 | Huy
10 | Class Management | 5 | Tấn Tài
11 | Course Management | 5 | Huy
12 | Subject Management | 5 | Hữu Tài
13 | Examination Management (Create,Update) | 6 | Hữu Tài